90 DAYS OUT

- Secure rooms (80 or more for Friday)

- Connect with important people on your campus

  - Campus police

  - Someone to unlock the rooms

  - Custodial service

- Request parking permits for TAB staff (12-15 for each day

- Identify a Tournament Director

- Work on getting WiFi access

- Talk to PSCFA Secretary/Treasurer/Tournament Director to determine who is bringing supplies

45 DAYS OUT

- Identify what rooms you will be using for

  - Tab

  - Extemp prep/IPDA topic strike

  - Student wellness

  - Judges room

  - Ballot stuffing/volunteer room

  - Fee collection

  - Room for awards

- Send the following information to the Tournament Director

  - Area map showing access routes to the college

  - Campus map

  - Where tournament headquarters will be

- Identify clerical volunteers (5-10 needed each day)

  - Food Runners

  - Ballot stuffers

  - General assistants

  - IPDA/Extemp head

TWO WEEKS BEFORE

- Start shopping for snacks/food for judges and student wellness. NOTE: per PSCFA Rules and Procedures, vegetarian-friendly meals must also be included in wellness planning.

  - You are guaranteed a certain amount of money for each tournament as a base for wellness. Use this amount as your guideline to determine what you are buying before you get your official amount from the PSCFA Treasurer

    - Champs: $1200 for judges, $500 for students

    - Warm Up: $600

    - Cool Off: $800

  - Waters

  - Utensils

  - Plates and serving utensils

  - sodas

- Double check the number of rooms you have secured

- If you are using EZ Cater start thinking about what orders you will place

WEEK OF

- Work with PSCFA Treasurer/Secretary to determine how much wellness money you will receive

- Work with PSCFA Treasurer to determine a trophy delivery location

- Secure what you will be serving for each day as meals

- Send out any announcements about WiFi, tournament headquarters, unique things on your campus (food and drink restrictions in rooms, rooms that are very far away, weather concerns, parking costs)

DURING THE TOURNAMENT RESPONSIBILTIES

- Ballots

  - Stuffing

  - Copying

  - Creating ballot packets

- Food – See Wellness (p.5-6)

  - Order/pick up all food during the tournament

  - Restock judges room and student wellness

    - Appoint volunteers to hang out in each room to replenish

  - Make sure you have enough serving items to cover the day

  - Have food arrive/distributed between rounds

  - Make sure you have ice (if needed)

- Tournament requirements

  - IPDA prep

  - Extemp Prep

  - Set up awards

  - Put up postings

  - Make/refresh copies of schedules and maps

- Housekeeping

  - Take out trash

  - Break down registration areas

  - Make sure rooms are unlocked

  - Lock rooms when done with buildings

  - Volunteer wrangling

OFFICE SUPPLIES

Work with PSCFA secretary/treasurer and Tournament Director to determine what supplies are needed from the host school. PSCFA can reimburse any office supplies bought expressly for the tournament

These costs are NOT included in the wellness money. Please keep these receipts separate from wellness receipts (food and food supplies)

- Two printers

- Two computers (at least)

- Ink cartridges for the printers

- 8 reams of white paper

- 8 reams of colored paper (typically yellow or blue)

- 2 boxes of pens

- 3 sharpies

- 1 box of pencils

- 10 boxes of paperclips

- 3 pair of scissors

- Large manila envelopes (at least 9x12 size with a closeable top)

- 100 manila file folders

- 8 rolls blue painters tape or masking tape

- White board markers or chalk

Wellness

GENERAL RULES OF THUMB FOR FOOD WELLNESS

- There are two budgets: student wellness and coach wellness

- You should strive to use the entirety of both budgets as that money can ONLY be spent on wellness

- It is better to err on the side of more food than less food. Hand held snacks are best as the extra food as people can take it to go and into awards. Think granola bars, fruit snacks, crackers, etc.

- The PSCFA secretary and treasurer are your contact points for how much money you will have for the tournament.

- Always have food orders ready to go BEFORE the start of a round. For example, if the round starts at 12:30 have lunch arrive and set up by Noon.

- At least one meal per day for students is encouraged.

- Some variety in food is appreciated

- You need a vegetarian option for at least 25 PEOPLE each meal

- Tab staff may request additional food/beverage. This cost is NOT included in overall wellness. Please keep these receipts separate if possible.

Times to have lunch/dinner prepped based on the 2018 Champs tournament schedule

| DAY | TIME | FOOD TYPE | JUDGES | STUDENTS |
| --- | --- | --- | --- | --- |
| FRIDAY | 10AM | SNACKS | X | X |
|  | 1PM | LUNCH | X | X (or more snacks) |
|  | 4:15 | DINNER | X | X |
| SATURDAY | 8AM | BRKFST | X | X |
|  | 1PM | LUNCH | X | X (or more snacks) |
|  | 4:30pm | DINNER | X | X |
| SUNDAY | 8am | BRKFST | X | X |
|  | 1PM | LUNCH | X | X (or more snacks) |
|  | 4PM | DINNER | X | X |

(All quantities based on amount needed for each day)

BREAKFAST IDEAS

- Bagels (1/2 per person)

- Cream cheese

- Muffins (1/2 per person)

- Breakfast pastries

- Nature Valley bars/granola bars

- Fruit (1 piece per person)

- Coffee (1 traveler for 25 people)

MEAL IDEAS

- Pizza (3 slices per person)

- Chipotle (ask for half burritos. One half burrito per person)

- Panda express (1 tray per 10 people per entrée)

- EZ Cater

  - This is a third party program that will list a bunch of caterers in your area. You can choose price range, number of people and time of delivery.

  - They will deliver to the tournament

  - This should be ordered a week in advance based off of estimated tournament numbers

  - You will need a credit card to order

- Subway or other sandwich place (6 inch sandwich per person)

SNACK IDEAS

- Granola bars (2 per person)

- Chips (2 snack bags per person)

- Cookies (2 per person)

- Waters (3 bottles per person)

  - One recommendation is to use the 8oz bottles so that you don’t have a lot of half empty bottles laying around

- Sodas (diet coke, coke, sprite) usually two per person

- Fruit (1 piece per person)

- Fruit snacks (1 pack per person)

- Goldfish (1 pack per person)

- Candy or sweet treat for afternoon

Food supplies

- Serving utensils

- Forks/knives

- Napkins

- Paper towels

- Plates/to-go containers

  - Styrofoam to-go containers are cheaper than plates at smart and final and then judges can take food to their next round without fear of spilling